## Task_Table
Teammate | Milestone | Duration | Start Date | Finish Date | Notes
All | UtmostU Data Analytics Project | 1 quarter
All | Project Kickoff | 1 day | 2021-06-07 | 2021-06-07
AH | Set up project plan
| Business Understanding | 1 day | 2021-06-07 | 2021-06-07
| Define Objectives | 1 day | 2021-06-07 | 2021-06-07 | Work with your customer and other stakeholders to understand and identify the business problems. Formulate questions that define the business goals and that data science techniques can target.
| Identify the key variables | Ongoing |  |  | A central objective of this step is to identify the key variables that the analysis needs to predict. These variables the ones that UtmostU wants to predict with respect to beneficiary success, but we need to define what success looks like.
AH | Define Project Goals | 1 day |  |  | Define the project goals by asking and refining "sharp" questions that are relevant and specific and unambiguous. Data science is the process of using names and numbers to answer such questions. ...
| Define success metrics | 1 day |  |  | Define success metrics. For example: Achieve student success prediction accuracy of X% by the end of this 3-month project, so that we can offer recommendations to UtmostU
| Identify Data Sources | Ongoing |  |  | Most of these will be the datasets provided, but if we need more, we can seek it out (for example, census data).
| Data Sources Documented | 1 day |  |  | This is the data sources that we will add to the Data Definitions they gave us
| Charter Document Delivered | 3 days |  |  | There is a standard template provided here: https://github.com/Azure/Azure-TDSP-ProjectTemplate/blob/master/Docs/Project/Charter.md. Do we want to do this?
| Ingest the data | Ongoing | 2021-06-18 |  | This does not need to be automated.
ALL | Explore the data | Ongoing | 2021-06-18 |  | EDA to develop a sound understanding of the data. Corrections for distrubution, noisy or missing data, other discrepancies. We have started this on our own already.
| Set up data pipeline | Ongoing |  |  | In addition to the initial ingestion and cleaning of the data, we might want to set up a process to score new data or refresh the data regularly as part of an ongoing learning process. This can be done by setting up a data pipeline or workflow.
| Experiment with Models | 1 day |  |  | Includes scoring, determining how to shape our data based on that scoring, experimenting with predictions on new data, your standard data science lifecycle steps
AH | Checkpoint With UtmostU | 1 day |  |  | Before we begin full feature engineering (PCA, etc.) and model building, we will reevaluate the project to determine whether the value expected is sufficient for UtmostU. This is the time where we will have the discussion about needing more data, changing our thinking on the models, etc.
| Select and design model | Ongoing |  |  | Collaboratively and and organically, we will choose the model(s) that we think work best for this project
| Feature Engineering | Ongoing |  |  | Feature engineering involves inclusion, aggregation and transformation of raw variables to create the features used in the analysis. If you want insight into what is driving a model, then you need to understand how features are related to each other and h
| Train Model | 1 day |  |  | Depending on type of question you are trying answer, there are many modeling algorithms available. The process for model training includes the following steps: ...
| Evaluate Model | 1 day |  |  | Evaluate (training and test dataset) a series of competing machine learning algorithms along with the various associated tuning parameters (known as parameter sweep) that are geared toward answering the question of interest with the current data
| Define Feature Sets | 1 day |  |  | The features developed for the modeling are described in the Feature Sets section of the Data Definition report. It contains pointers to the code to generate the features and description on how the feature was generated....
| Create Model Report | 3 days |  |  | For each model that is tried, a standard, template-based report that provides details on each experiment is produced....
| Checkpoint | 1 day |  |  | Evaluate whether the model is performing well enough to deploy it to a production system. Some key questions to ask are:...
| Operationalize the Model | 5 days |  |  | Once we have a set of models that perform well, we want to operationalize it for other applications to consume. Basically this is about letting UtmostU run new predictions in real-time or on a periodic basis.
| Finalize Report | 5 days |  |  | Create a status dashboard or report of the key metrics
All | Deliver final modeling report | 1 day |  |  | Create a final modeling report with deployment details.
AH | Project Handoff | 0 days |  |  | A hand-off of the project to David Bennet of UtmostU. This would also be a good time to make sure you have a personal copy of everything stored in GitHub for your own portfolio (useful for career progression)
All | Project Close-out: Exit Report of Project for Customer | 0 days |  |  | Document all details of the project that will be useful for us and for UtmostU to learn about and operate the system. We should document this for them and for ourselves.

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Business | Bz | Work |  |  |  |  | 100% | $0.00/h | 0
2 | IT Director | Di | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Data Engineer | De | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Data Scientist | Ds | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Front End Developer | Fe | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Visualization | Vi | Work |  |  |  |  | 100% | $0.00/h | 0
7 | Tester | Te | Work |  |  |  |  | 100% | $0.00/h | 0
8 | DevOps | Do | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Project Kickoff | Business | 0 | 8h | 100%
Project Kickoff | Data Scientist | 0 | 8h | 100%
Project Kickoff | DevOps | 0 | 8h | 100%
Business Understanding | Business | 0 | 64h | 100%
Business Understanding | Data Scientist | 0 | 64h | 100%
Define Objectives | Business | 0 | 8h | 100%
Identify the key business variables | Business | 0 | 8h | 100%
Identify the key business variables | Data Scientist | 0 | 8h | 100%
Identify the key business variables | Data Engineer | 0 | 8h | 100%
Define Project Goals | Business | 0 | 8h | 100%
Define Project Goals | Data Scientist | 0 | 8h | 100%
Define Project Goals | IT Director | 0 | 8h | 100%
Define project team | IT Director | 0 | 8h | 100%
Define success metrics | IT Director | 0 | 8h | 100%
Define success metrics | Business | 0 | 8h | 100%
Define success metrics | Data Scientist | 0 | 8h | 100%
Identify Data Sources | Business | 0 | 40h | 100%
Identify Data Sources | Data Engineer | 0 | 40h | 100%
Identify Data Sources | Data Scientist | 0 | 40h | 100%
Identify Data Sources | DevOps | 0 | 40h | 100%
Identify Data Sources | Visualization | 0 | 40h | 100%
Identify Data Sources | IT Director | 0 | 40h | 100%
Data Sources Documented | Data Engineer | 0 | 0h | 100%
Data Sources Documented | Data Scientist | 0 | 0h | 100%
Data Sources Documented | DevOps | 0 | 0h | 100%
Data Dictionaries Delivered | Data Engineer | 0 | 0h | 100%
Data Dictionaries Delivered | Data Scientist | 0 | 0h | 100%
Data Dictionaries Delivered | DevOps | 0 | 0h | 100%
Charter Document Delivered | Data Scientist | 0 | 0h | 100%
Charter Document Delivered | Data Engineer | 0 | 0h | 100%
Charter Document Delivered | DevOps | 0 | 0h | 100%
Charter Document Delivered | IT Director | 0 | 0h | 100%
Ingest the data | Data Engineer | 0 | 24h | 100%
Explore the data | Data Engineer | 0 | 24h | 100%
Explore the data | Data Scientist | 0 | 24h | 100%
Explore the data | Front End Developer | 0 | 24h | 100%
Explore the data | Visualization | 0 | 24h | 100%
Set up data pipeline | Data Engineer | 0 | 8h | 100%
Set up data pipeline | DevOps | 0 | 8h | 100%
Deliver Data Quality Report | Data Engineer | 0 | 0h | 100%
Deliver Data Quality Report | Data Scientist | 0 | 0h | 100%
Deliver Data Quality Report | DevOps | 0 | 0h | 100%
Deliver a Solution Architecture | Data Scientist | 0 | 0h | 100%
Deliver a Solution Architecture | DevOps | 0 | 0h | 100%
Checkpoint Decision | Data Scientist | 0 | 0h | 100%
Checkpoint Decision | Business | 0 | 0h | 100%
Feature Engineering | Data Engineer | 0 | 8h | 100%
Feature Engineering | Data Scientist | 0 | 8h | 100%
Train Model | Data Scientist | 0 | 8h | 100%
Evaluate Model | Data Scientist | 0 | 8h | 100%
Define Feature Sets | Data Scientist | 0 | 8h | 100%
Create Model Report | Data Scientist | 0 | 8h | 100%
Checkpoint Decision | Data Scientist | 0 | 8h | 100%
Checkpoint Decision | IT Director | 0 | 8h | 100%
Checkpoint Decision | Business | 0 | 8h | 100%
Deployment | Data Engineer | 0 | 8h | 100%
Deployment | Data Scientist | 0 | 8h | 100%
Deployment | DevOps | 0 | 8h | 100%
Deployment | Front End Developer | 0 | 8h | 100%
Deployment | Tester | 0 | 8h | 100%
Deployment | Visualization | 0 | 8h | 100%
Operationalize the Model | DevOps | 0 | 8h | 100%
Operationalize the Model | Data Engineer | 0 | 8h | 100%
Operationalize the Model | Data Scientist | 0 | 8h | 100%
Operationalize the Model | Front End Developer | 0 | 8h | 100%
Operationalize the Model | Tester | 0 | 8h | 100%
Operationalize the Model | Visualization | 0 | 8h | 100%
Deliver status dashboard | Visualization | 0 | 0h | 100%
Deliver status dashboard | DevOps | 0 | 0h | 100%
Deliver status dashboard | Data Scientist | 0 | 0h | 100%
Deliver final modeling report | Data Scientist | 0 | 0h | 100%
Deliver final modeling report | DevOps | 0 | 0h | 100%
Deliver final modeling report | IT Director | 0 | 0h | 100%
Deliver Final solution architecture document | Data Scientist | 0 | 0h | 100%
Deliver Final solution architecture document | DevOps | 0 | 0h | 100%
System Validation | IT Director | 0 | 8h | 100%
System Validation | Data Scientist | 0 | 8h | 100%
System Validation | Tester | 0 | 8h | 100%
System Validation | DevOps | 0 | 8h | 100%
Project Handoff | IT Director | 0 | 8h | 100%